## Sheet1
Phase | Task ID | Task Name | Description | Assigned To | Start Date | End Date | Duration (Hours) | Predecessors | Dependencies | Status
Initiation & Planning | 1.1 | Review Project Requirements | Analyze and document system requirements | Student | Day 1 | Day 1 | 2 | - | Project Brief | Not Started
Initiation & Planning | 1.2 | Define Project Milestones | Outline key deliverables: Documentation, UML Diagram, Project Plan, GUI. | Student | Day 1 | Day 1 | 1 | 1.1 | - | Not Started
Design & Documentation | 2.1 | Draft System Documentation | Write a 400-500 word report explaining design choices, database structure, GUI layout, and assumptions. | Student | Day 2 | Day 3 | 6 | 1.2 | - | Not Started
Design & Documentation | 2.2 | Create UML Class Diagram | Design a UML diagram showing Classes (e.g., User, Claim, Document), their attributes, and relationships. | Student | Day 2 | Day 3 | 4 | 1.2 | - | Not Started
Design & Documentation | 2.3 | Finalize Project Plan | Create and submit the detailed project plan (this spreadsheet). | Student | Day 3 | Day 3 | 2 | 1.2 | Excel/Sheets | Not Started
GUI Development | 3.1 | Set Up Development Environment | Install and configure .NET Core SDK and chosen IDE (e.g., Visual Studio). | Student | Day 4 | Day 4 | 2 | 1.2 | IDE & .NET Install | Not Started
GUI Development | 3.2 | Initialize Git Repository | Create local repo and connect to the provided GitHub repository. Make first commit. | Student | Day 4 | Day 4 | 1 | 3.1 | GitHub Access | Not Started
GUI Development | 3.3 | Create Base Project Structure | Create a new WPF or MVC project and set up basic folder structure (Models, Views, Controllers). | Student | Day 4 | Day 4 | 2 | 3.2 | - | Not Started
GUI Development | 3.4 | Design Login View | Create a non-functional login screen with fields for username and password. | Student | Day 5 | Day 5 | 3 | 3.3 | - | Not Started
GUI Development | 3.5 | Design Lecturer Dashboard View | Create a view with a button to "Submit New Claim" and a table to "Track Claim Status". | Student | Day 6 | Day 6 | 4 | 3.4 | - | Not Started
GUI Development | 3.6 | Design Claim Submission Form | Create a form with fields for claim details and a button to "Upload Supporting Documents". | Student | Day 7 | Day 7 | 4 | 3.5 | - | Not Started
GUI Development | 3.7 | Design Coordinator/Manager Dashboard | Create a view with a list of claims for verification/approval with buttons for those actions. | Student | Day 8 | Day 8 | 4 | 3.4 | - | Not Started
GUI Development | 3.8 | Apply Basic Styling | Ensure UI is clean, consistent, and intuitive (non-functional). | Student | Day 9 | Day 9 | 3 | 3.5, 3.6, 3.7 | - | Not Started
Version Control | 4.1 | Commit & Push (1/5) | Push initial project setup and login view. Write clear commit message. | Student | Day 4 | Day 4 | 0.5 | 3.3, 3.4 | - | Not Started
Version Control | 4.2 | Commit & Push (2/5) | Push progress on Lecturer Dashboard. Write clear commit message. | Student | Day 6 | Day 6 | 0.5 | 3.5 | - | Not Started
Version Control | 4.3 | Commit & Push (3/5) | Push the Claim Submission Form. Write clear commit message. | Student | Day 7 | Day 7 | 0.5 | 3.6 | - | Not Started
Version Control | 4.4 | Commit & Push (4/5) | Push the Coordinator Dashboard. Write clear commit message. | Student | Day 8 | Day 8 | 0.5 | 3.7 | - | Not Started
Version Control | 4.5 | Commit & Push (5/5) | Final push with all styled views and final code. Write clear commit message. | Student | Day 9 | Day 9 | 0.5 | 3.8 | - | Not Started
Final Compilation & Submission | 5.1 | Final Review & Compile Report | Combine documentation, UML diagram, and project plan into a single Word document. | Student | Day 10 | Day 10 | 3 | 2.1, 2.2, 2.3 | Microsoft Word | Not Started
Final Compilation & Submission | 5.2 | Final Git Push & Submission | Push any final changes. Submit the Word document report as required. | Student | Day 10 | Day 10 | 1 | 4.5, 5.1 | - | Not Started